## Sheet1
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-hour) | Start Date | End Date | Remarks
Week 1
| 1. Project Planning | 1.1. Project understanding with clear vision | 1.1.1 Collecting anlyse data | 4 | 2023-07-03 | 2023-07-03 | Done
|  |  | 1.1.2 Understanding scope and objectives | 4 | 2023-07-04 | 2023-07-04 | Done
|  | 1.2. WBS | 1.2.1 Identify project deliverables and activities | 2 | 2023-07-03 | 2023-07-05 | Done
|  |  | 1.2.2 Task breakdown | 4 | 2023-07-04 | 2023-07-05 | Done
|  |  | 1.2.3 Create WBS with time estimates | 2 | 2023-07-04 | 2023-07-07 | Done
| 2. Project Design | 2.1 Design Documents | 2.1.1 Manual Deployment Architecture Design | 8 | 2023-07-04 | 2023-07-05 | Done
|  |  | 2.1.2 On Premise Deployment Architecture Design | 8 | 2023-07-04 | 2023-07-06 | Done
|  |  | 2.1.3 AWS Deployment Architecture Design | 8 | 2023-07-06 | 2023-07-07 | Done
Week 2
| 3. Manual Deployment | 3.1 Server preparation | 3.1.1 Prepare virtual machine | 1 | 2023-07-10 | 2023-07-10 | Pending
|  |  | 3.1.2 Install and configure Java and MySQL | 2 | 2023-07-10 | 2023-07-10 | Pending
|  | 3.2 Code deployment | 3.2.1 Configure database settings | 1 | 2023-07-11 | 2023-07-12 | Pending
|  |  | 3.2.2 Manage code | 0.5 | 2023-07-10 | 2023-07-12 | Pending
|  |  | 3.2.3 Manual deployment | 1.5 | 2023-07-10 | 2023-07-13 | Pending
| 4. On Premise Server Provision and deployment | 4.1 Server preparation | 4.1.1 Prepare three virtual machines | 1 | 2023-07-11 | 2023-07-14 | Pending
|  |  | 4.1.2 Install required softawes in the virtual machine | 3 | 2023-07-11 | 2023-07-14 | Pending
|  |  | 4.1.3 Configure Kubernetes | 4 | 2023-07-12 | 2023-07-14 | Pending
|  | 4.2 Create CI/CD pipeline | 4.2.1 Create CI | 3 | 2023-07-12 | 2023-07-13 | Pending
|  |  | 4.2.2 Create a Jenkins pipeline for k8s | 4 | 2023-07-12 | 2023-07-13 | Pending
|  |  | 4.2.3 Perform issue debugging | 1 | 2023-07-12 | 2023-07-14 | Pending
| 5. AWS Server Provision and deployment | 5.1 Infrastucture provisioning | 5.1.1 Create a VPC network for the infrastructure | 1 | 2023-07-12 | 2023-07-14 | Pending
|  |  | 5.1.2 Create RDS and perform necessary settings | 2 | 2023-07-12 | 2023-07-13 | Pending
|  | 5.2 Deploy with CI/CD | 5.2.1 Create Jenkins pipeline | 4 | 2023-07-13 | 2023-07-14 | Pending
|  |  | 5.2.2 Deploy Application | 1 | 2023-07-13 | 2023-07-14 | Pending
Week 3
| 6. EKS Deployment | 6.1 Analyse Requirerments | 6.1.1 Understanding EKS architecture | 5 | 2023-07-17 | 2023-07-18 | Pending
|  |  | 6.1.2 Determine required managed services | 3 | 2023-07-17 | 2023-07-18 | Pending
|  | 6.2 Create document of step by step guide | 6.2.1 Create architecture diagram | 5 | 2023-07-17 | 2023-07-19 | Pending
|  |  | 6.2.2 Documenting explanation of deployment process | 6 | 2023-07-18 | 2023-07-20 | Pending
| 7. Maintain in a Git repository | 7.1 Code Maintainance | 7.1.1 Create and manage a repository | 3 | 2023-07-10 | 2023-07-21 | Pending
|  |  | 7.1.2 Initiate, commit and push codes | 3 | 2023-07-10 | 2023-07-21 | Pending
|  | 7.2 Created and maintained Readme file | 7.2.1 Create and maintai a Readme file | 3 | 2023-07-10 | 2023-07-21 | Pending
| 8. Presentation & documentation preparation | 8.1 Project Documentation praparation | 8.1.1 Prepare project documentation | 6 | 2023-07-10 | 2023-07-21 | Pending
|  | 8.2. Project presentation preparation | 8.2.1. Project presentation preparation | 6 | 2023-07-10 | 2023-07-21 | Pending
Week 4
| Project submission & Project demonstration | [5 empty] | Pending